## Worksheet 1
AAF-supported field campaigns | Challenges and data collection limitations
Biomass Burning Observation Project (BBOP), 2013 | Air traffic control regulations and safety concerns limited the ability to sample immediately after emissions; therefore, the focus was instead on measurements 15 min to several hours post-emission. Due to the high aerosol number concentrations in the fire plumes, most instruments were operated near their upper limits. Post-processing was implemented to minimize the coincidence problem with the particle counting but could not entirely eliminate the issue.
Observations and Modeling of the Green Ocean Amazon (GoAmazon), 2014 | The Amazon Rainforest experiences frequent cloud cover and heavy rainfall, which significantly interfered with flight planning and the number of viable data collection periods. The Amazon's high humidity and frequent rainfall can negatively affect airborne instruments and sensors. Thus, a dryer system was integrated into the inlet system to ensure aerosol data collection under dry conditions.
ARM Cloud Aerosol Precipitation Experiment (ACAPEX), 2015 | Few ARs made landfall in northern California during the campaign, and many days had clear skies; this limited the opportunities to study aerosol–cloud–precipitation interactions. While flying through heavy precipitation, water accumulation in cloud probes posed difficulties with respect to accurate measurement collection. Some archived data had to be flagged during post-processing.
Airborne Carbon Measurements (ACME V), 2015 | Dense fog and low-elevation clouds in September limited flight operations over coastal sites, affecting data collection during this period. Aerosol measurements were limited due to deployment and budget restrictions in the Arctic environment during this campaign.
Holistic Interactions of Shallow Clouds, Aerosols, and Land-Ecosystems (HI-SCALE), 2016 | The G-1 aircraft operations were based at a location 150 km away from the ARM SGP central facility, which resulted in extra flight hours during transit. The hot weather posed an additional challenge, reducing flight time and affecting the optimal flight times during the day. Another challenge was the aircraft's payload capacity, a common issue for all research aircraft, as we aimed to carry more instruments than the aircraft could accommodate. As a result, we had to sacrifice some optical measurements to stay within the payload limits.
Aerosol and Cloud Experiments in the Eastern North Atlantic (ACE-ENA), 2017 and 2018 | The eastern North Atlantic frequently experiences rough weather, including high winds, storms, and turbulence, posing significant challenges for flight operations. Occasional impacts of anthropogenic emissions from Graciosa Island on G-1 measurements were experienced, especially at the lowest sampling altitudes. Terrain blockage limited the coordination of scanning cloud radar operation and G-1 sampling when the wind was oriented in certain directions. (One major feature of ACE-ENA is the synergy between G-1 measurements and observations at the ENA site.) The air space access is restricted near the ground (ENA) site due to incoming and outgoing commercial flights.
Cloud, Aerosol, and Complex Terrain Interactions (CACTI), 2018 | The intricate interactions between the boundary layer, orographic, low-level jet, and frontal circulations produced tremendous variability in aerosol and cloud conditions. Some other challenges included (1) the safety risk from intense, quickly evolving storms in the vicinity of the flying aircraft and hangar; (2) clouds intersecting or being close to high terrain, making it impossible to sample the cloud base; (3) power outages, which raised concerns about ice-nucleating particle filters thawing during storage; and (4) weather warnings, such as icing conditions.